## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Collect financial document datasets, including salary slips and profit/loss statements,checks using Web Scraping. | MUST HAVE | Beautiful Soup | Self | 3- Completed
S1 | S1 | US-001 | Research and set up a secure cloud storage solution for storing sensitive financial documents. | SHOULD HAVE | AWS S3 setup | Self | 3- Completed
S2 | S2 | US-002 | Extract text using OCR technologies (PaddleOCR, EasyOCR) and visualize extracted text. | MUST HAVE | OCR libraries installations | Self | 3- Completed
S2 | S2 | US-002 | Conduct accuracy and speed benchmarking for the selected OCR tools. | MUST HAVE | None | Self | 3- Completed
S3 | S3 | US-003 | Extract fields from financial documents using PaddleOCR and LLM and visualize data. | MUST HAVE | PaddleOCR and LLM integration | Self | 3- Completed
S3 | S3 | US-003 | Develop and validate templates for extracting structured information from financial documents. | SHOULD HAVE | OCR output preprocessing pipeline | Self | 3- Completed
S4 | S4 | US-004 | Provide a user interface for querying financial data and retrieving contextual responses from the LLM. | MUST HAVE | LLM integration | Self | 3- Completed
S4 | S4 | US-004 | Build and deploy the final OCR application for end-to-end financial document analysis. | MUST HAVE | Complete pipeline integration | Self | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 41 | 20 | 16 | 1900-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT BACKLOG
US-001 | TID-01 | Collect financial document datasets, including salary slips and profit/loss statements,checks using Web Scraping. | 2024-11-04 | 2024-11-09 | Self | Others | 3- Completed | 3 | Day 1: 2; Day 2: 1; Day 3: 0
US-001 | TID-02 | Research and set up a secure cloud storage solution for storing sensitive financial documents. | 2024-11-12 | 2024-11-15 | Self | Build | 3- Completed | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-002 | TID-03 | Extract text using OCR technologies (PaddleOCR, EasyOCR) and visualize extracted text. | 2024-11-18 | 2024-11-23 | Self | Coding | 3- Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0
US-002 | TID-04 | Conduct accuracy and speed benchmarking for the selected OCR tools. | 2024-11-25 | 2024-11-29 | Self | Unit Test | 3- Completed | 3 | Day 1: 1; Day 2: 2; Day 3: 1
US-003 | TID-05 | Extract fields from financial documents using PaddleOCR and LLM and visualize data. | 2024-12-02 | 2024-12-06 | Self | Coding | 3- Completed | 6 | Day 1: 3; Day 2: 2; Day 3: 1
US-003 | TID-06 | Develop and validate templates for extracting structured information from financial documents. | 2024-12-09 | 2024-12-13 | Self | Unit Test | 3- Completed | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-004 | TID-07 | Provide a user interface for querying financial data and retrieving contextual responses from the LLM. | 2024-12-16 | 2024-12-20 | Self | Build | 3- Completed | 5 | Day 1: 3; Day 2: 2; Day 3: 0
US-004 | TID-08 | Build and deploy the final OCR application for end-to-end financial document analysis. | 2024-12-23 | 2024-12-27 | Self | Coding | 3- Completed | 10 | Day 1: 5; Day 2: 3; Day 3: 2

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Cloud Storage Setup Challenges: | Learned AWS IAM policies and configured secure API access
Sprint 1 | Day 4 | Dataset Quality Issues | Filtered out low quality images
Sprint 2 | Day 17 | OCR Technology Evaluation Complexity | Conducted detailed comparative testing on diverse sample documents.
Sprint 2 | Day 19 | Field Extraction Inconsistencies | Fine-tuned field identification logic with iterative testing on varied layouts.
Sprint 4 | Day 26 | Limited Control Over LLM Responses | Validated and refined outputs
Sprint 4 | Day 33 | Integration Complexity | Debugged and streamlined data flow between OCR, LLM, and visualization components.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-04 | 2024-11-09 | Adwait Salankar | Researching cloud storage options | Relying solely on local storage | Relying solely on local storage | Configured Amazon S3 for secure dataset storage and implemented AWS API calls.
2 | Sprint 2 | 2024-11-18 | 2024-11-23 | Adwait Salankar | Using manual methods for text extraction | Using manual methods for text extraction | Fine-tuning preprocessing and field extraction logic | Conducted comparative analysis of PaddleOCR, and EasyOCR to finalize the most suitable tool
3 | Sprint 3 | 2024-12-16 | 2024-12-20 | Adwait Salankar | Relying on static extraction methods | Relying on static extraction methods | Fine-tuning preprocessing and field extraction logic | Implemented field extraction automation for financial and salary-related data.
4 | Sprint 4 | 2024-12-16 | 2024-12-20 | Adwait Salankar | Integrating LLM for user queries | Limited integration of tools in separate modules | Improving field extraction accuracy and handling noisy images | Integrated OCR, LLM, and visualization tools into a unified pipeline with user query functionality.